## Slide 1
The Pathway to Success
Enhance the Gathering
and Use of Information
Goal 1 – Initiative 9
Notes: Good morning – thanks
Getting close to lunch
New
Gathering and Using

## Slide 2: Accomplishments Since 2013-14 Report
Blue Reports Phase 1 Release
Large CRM effort to support Distance Marketing Effort
Areas working to increase availability and variety of CC Data in Banner

## Slide 3: Benchmark Table

## Slide 4: Benchmark Progress Detail
CC Data areas still being added
CC Dashboards – Fall 2015
Academic Dashboards – Fall 2015
Internships – Tracked internally at CCE
Departments Using CRM – Full Speed Ahead
Colleges Tracking and Using Attendance – Great Progress

## Slide 5: Budget Summary
Total funding allocation for 2014-15: $90,000
Expenses as of report date
  Expenditures: $36,000
  Encumbered costs: $51,000
Anticipated remainder June 30, 2015
  $30,000

## Slide 6: Accomplishments Since Plan Inception
Campus culture much more data oriented
28 Areas now tracking CC Data
Data Warehouse implemented
Data Warehouse rebooted
CRM going Enterprise Wide
Attendance tracking being aggressively investigated/piloted

## Slide 7: Baseline Recommendation
Tightly integrated with IT and IR
Some budget has been integrated
Initiative should remain active
  Nature of technology
  State of internal knowledge
  President Bradley

## Slide 8: Looking Ahead - Recommendations
CRM
  Must keep our project resources focused on expanding adoption of Blue Reports and CRM
Blue Reports
  Enrollment Data/Retention Data/Graduation Data is available
  Must continue improving collection and report of CC Data/Career Data
Attendance
  Tracked and available as part of student profile
    Blue Reports? MapWorks? Banner?

## Slide 9: New points of emphasis
Blue Reports – Get the word out
Required usage:
  Blackboard
  Attendance taking
CRM
  Graduate and Professional Studies
  Sycamore Express

## Slide 10: Foreseeable Roadblocks
Adoption
Competing Priorities
Technology
Cost

## Slide 11: Missed opportunities
Timing?
Knowledge?

## Slide 12: Questions?
Enhance the Gathering and Use of Information
Mike Snyder
mike.snyder@indstate.edu