## Slide 1
The Pathway to Success
Pre-College
Goal 1 – Initiative 11a
Notes: Good morning – thanks
Getting close to lunch
New
Gathering and Using

## Slide 2: Accomplishments Since 2013-14 Report
Tuition assistance for high school teachers (9 teachers, 54 credit hours)
College+You early outreach website soft rollout (Phase II updates in progress adding more pictures, video, and interactive features)
Early prospecting mailing planned for April

## Slide 3: Benchmark Table

## Slide 4: Benchmark Progress Detail
Increase College Challenge Enrollment- Projected to reach 1,950 (goal 1,900)
Increase College Challenge Credits- projected at 5,300 (goal 5,219)
Increase Freshman Enrollment- 26% increase since 2008
Early Outreach Events- 10 events on campus by June 1.

## Slide 5: Budget Summary
Total funding allocation for 2014-15: $66,816
Expenses as of report date
  Expenditures- tuition assistance: $17,708, website: $93.02
  Encumbered costs- website: $5000, tuition assistance: $13,000, early pros. mailing $31,000
Anticipated remainder June 30, 2015: $14.00

## Slide 6: Accomplishments Since Plan Inception
College+You website targeting 12-14yo
College Challenge class visits- 388 attendees
New marketing materials, mailings, and e-communications
Expansion of College Challenge partnerships by offering teacher tuition assistance

## Slide 7: Looking Ahead - Recommendations
Continue tuition assistance for teachers
COLLEGE+YOU marketing plan for roll-out of phase II of new website
Early Prospect Mailing should be base lined to Admissions with a budget allocation
Develop curriculum use for COLLEGE+YOU website and additional content development

## Slide 8: Foreseeable Roadblocks
Budget funding
Evolving technology and the ways students connect and gather information
Changing perceptions in how information pushed out by the University is perceived by young students

## Slide 9: New points of emphasis
Collaboration with school administrators to advance curricular development and integrate COLLEGE+YOU website and other tools into daily school activities
Partner with statewide initiative to develop county based college success coalitions

## Slide 10: Missed opportunities
Develop plan to include pre-college initiatives in the annual Counselor Day on Campus event. Great opportunity to engage, collaborate, and get input from elementary, secondary and high school guidance counselors on our target population.

## Slide 11: Baseline Recommendation
The Early Prospect Mailing should be integrated into the operation of Admissions with a budget allocation to support its continued use. It has been funded through Initiative 11a for 3 consecutive years.

## Slide 12: Opportunities for Collaborations
There is potential to collaborate with Initiative 4- Parents and Families, to expand our impact on younger children and/or friends of our ISU parents and families.

## Slide 13: Questions?
Initiative 11a- Pre College
Jill Blunk- Jill.Blunk@indstate.edu
Rich Toomey- Richard.Toomey@indstate.edu