## Slide 1
The Pathway to Success
Co-Curricular Life
Brooks Moore
Freda Luers
Goal 1 – Initiative 12
Notes: Good morning – thanks
Getting close to lunch
New
Gathering and Using

## Slide 2: Accomplishments Since 2013-14 Report
Club Month: 80 Coordinated Programs
Icon and Legacy Series
  Homecoming: 13 Programs
  Sycamore Scare Week: 13 Programs, 1603 Students
  Heritage Week: 13 Programs, 1925 Students
  Spring Into State: 14 Programs, 2104 Students
  Sycamore Hoopla: 12 Programs, 2537 Students
  Mardi Gras: 1 Program, 226 Students
  Spring Week: 14 Programs, TBA – April 6 – 11
  Operation Beautiful: 4 Programs, 329 Students
Center for Global Engagement Partnership
Graduate Student Association: Transition with Graduate & Professional College advising
Faculty Led-Learning Trips: Partnership with Academic Colleges
Rez-Fest end-of-semester celebration: concert & music festival

## Slide 3: Benchmark Table

## Slide 4: Benchmark Progress Detail
# of Student Organizations
  2014: 304 2015: 304 (goal: 300)
# of events with > 500 students
2014: 20 2015: 24 (goal: 22)
Increase satisfaction/sense of belonging (MapWorks)
2014: 55% 2015: 62% (goal: 56)
62=Extremely; 28%=Moderately
Increase participation in campus organizations (MapWorks)
2014: 35% 2015: 36.5% (goal: 40)
36.5=Extremely; 28%=Moderately

## Slide 5: Budget Summary
Total funding allocation for 2014-15: $95,000
Expenses as of report date
  Expenditures: $63,000
  Encumbered costs: $32,000
Anticipated remainder June 30, 2015: $0

## Slide 6: Accomplishments Since Plan Inception
Expanded Club Week into Club Month
Enhanced support for Icon Programs (Homecoming, Hoopla, Spring Week)
Established Legacy Series
Strengthened Partnership with CGE

## Slide 7: Looking Ahead - Recommendations
Continue Club Month as critical first 30 days
Review Legacy Series to ensure student interest in theme-based programming
Expand audience and connections between students in partnered-CGE initiatives

## Slide 8: Foreseeable Roadblocks
Attendance tracking at open-access events
Maintaining effective communication between partners and collaborators
Remaining relevant in changing student interests
Breadth vs. Depth philosophical approach and which will benefit/impact students

## Slide 9: New points of emphasis
Expanding women’s development series
Expand cultural-based programming for new/emerging populations
Implement men’s development series
Highlight co-curricular development as offerings of student development needs and not just student activity programming

## Slide 10: Missed opportunities
Graduate student development
Partnership and collaboration with academic colleges
First year initiative with University College
Connect PAW concept with Legacy Series

## Slide 11: Baseline Recommendation
Has this initiative been sufficiently integrated into your operations?
Yes, this is the basis for our programmatic offerings.

## Slide 12: Opportunities for Collaborations
University College
Residential Life and Housing
University Apartments: Sophomore Experience
Graduate and Professional College
Academic Colleges and Departments
Sodexo

## Slide 13: Questions?
Goal 1: Initiative 12
Co-Curricular Life
Brooks Moore: brooks.moore@indstate.edu