**STRATEGIC PLANNING TIMELINE**

**Key Questions**

**Date Time Event Location**

|  |  |  |  |
| --- | --- | --- | --- |
| September 17, 2015 | 8:30 – 10:00 a.m. | First Meeting of the Steering committee | Parsons Hall, Room 210 |
| October 1, 2015 | 3:30 – 5:30 p.m. | Meeting of all Committee and Subcommittee Chairs | HMSU, Dede I |
| November 5, 2015 | 2:00 – 3:30 p.m. | Check-In Meeting #1 of all Committee Chairs | Tirey Ballroom |
| November 16, 2015 |  | Subcommittee Preliminary Reports Due |  |
| November 30, 2015 | 8:30 – 10:00 a.m. | Check-In Meeting #2 of all Committee Chairs | Tirey Ballroom |
| December 4, 2015 | 3:00 – 5:00 p.m. | Steering Committee Meeting | HMSU, Room 307 |
| January 11, 2016 |  | Key Questions Subcommittee Final Reports Due  Mission, Vision and Values Report Due |  |

**Goals and Benchmarks Development**

**Date Time Event Location**

|  |  |  |  |
| --- | --- | --- | --- |
| January 25, 2016 | 2:00 – 5:00 p.m. | Campus Town Hall Meeting | HMSU, Dede I |
|  | * Intro and review of progress achieved this far * Presentation of key points from each key question committee * Table discussion on key question committee findings and recommendations * Report out of key points from table discussions | | |
| January 28, 2016 | 1:00 – 3:00 p.m. | Steering Committee Meeting | HMSU, Room 307 |
|  | * Presentation of major planning parameters to steering committees * Discussion of key committee reports * Development of draft goal statements * Development of draft benchmarks for goal statements * Creation of task force(s) to quantify benchmarks | | |
| February 9, 2016 | 1:00 – 3:00 p.m. | Campus Town Hall Meeting | HMSU, Dede I |
|  | * Presentation of draft goals and benchmarks * Discussion | | |
| February 10, 2016 | 7:30 – 9:00 p.m. | Student Strategic Planning Session with SGA | HMSU Dede II |
| March 9, 2016 | 3:00 – 5:00 p.m. | Steering Committee Meeting | HMSU, Room 307 |
|  | * Benchmarks are quantified and documented * Discussion | | |
| March 30, 2016 | 1:00 – 4:00 p.m. | Steering Committee Meeting | HMSU, Room 307 |
|  | * Goal, benchmarks, and initiative committees are finalized. | | |
| April 6, 2016 | Canceled | Campus Stakeholders Meeting | Canceled |
|  | Canceled | | |
| April 27, 2016 | 3:00 – 5:00 p.m. | Campus Stakeholders Meeting | HMSU, Dede I |
|  | TBD | | |

**Initiatives Development**

|  |  |
| --- | --- |
| Summer 2016 | Initiatives Development |
| August 2016 | Master Plan Update Due |
| Fall 2016 | New Plan Announce at President’s Fall Address |

**Implementation**

|  |  |
| --- | --- |
| October 2016 | Implementation Begins |